## Road Map
BITEBUDDY PORTAL
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/26/2025 | SPRINT2 - 04/16/2025 | SPRINT3 - 05/07/2025
01.User Management | 01.01 Register User Account | 4 | X
| 01.02 Log In User | 4 | X
| 01.03 Manage User Profile | 4 | X
| 01.04 Control Role-Based Access | 4
| 01.05 View Order History | 3 |  | X
02. Restaurant Management | 02.01 List Restaurants | 1 | X
| 02.02 Search Restaurants | 1 | X
| 02.03 Browse Menu Items | 1 | X
| 02.04 Manage Restaurants Profile | 1 | X
| 02.05 Update Menu Offerings | 2 |  | X
| 02.06 Manage Table Reservations | 4 |  |  | X
03. Order and Payment Processing | 03.01 Place Food Order | 4 |  | X
| 03.02 Process Secure Payment | 4 |  |  | X
| 03.03 Track Commission Revenue | 4
| 03.04 Manage Refunds and Cancellations | 4 |  |  | X
| 03.05 Generate Financial Reports | 4 |  |  | X
04. Advertisement Management | 4.01 Create Ad Campaigns | 3 |  | X
| 4.02 manage Sponsored Listings | 3 |  | X
| 4.03 Track Ad Performance | 3
| 4.04 Update and Optimize content | 3 |  |  | X
05.Payment Gateway | 05.01 Manage Financial Account | 4
| 05.02 Generate Sales Reports | 4 |  |  | X
| 05.03 Process Payments | 4 |  |  | X
| 5.04 Ensure Compliance with Finacial regulations | 3
06. Platform Administration | 06.01 Manage User Accounts | 4
| 06.02 Monitor System Performance | 3
| 06.03 Resolve Technical Issues | 4
| 06.04 Deploy System Updates | 3
| 06.05 Ensure Compliance | 2
| 06.06 Manage Digital Advertisements | 2
| 06.07 Analyze Ad Performance | 3
07. Customer Support | 07.01 Track Order Status | 4 |  | X
| 07.02 Provide Chat Support | 3
| 07.03 Submit Feedback | 3 |  | X
| 07.04 Rate Restaurant Experience | 3
| 07.05 Manage FAQs | 2 |  | X
| 07.06 Manage Support Tickets | 4
|  | VELOCITY: | 16 | 24 | 27