## Sheet1
USER STORIES - BiteBuddy
Module | Title | As a/an | I want to… | So that I can… | Sprint | Story Points | Story Constraints | Story Exceptions
01. User Management | 01.01 Register User Account | Diner/Restaurant Owner/System Administrator | register by providing necessary details such as my name, email, phone number, and password. | create a user account and provide required access to the platform. | S1 | 4 | Must adhere to password complexity rules, validate email format, and check phone number formats. Passwords must be at least 8 characters long, with a combination of uppercase, lowercase, numbers, and symbols. | Field Validation (FV): Ensure all required fields are correctly filled and display instructive error messages for invalid input.
| 01.02 Log In User | Diner/Restaurant Owner/System Administrator/Platform Manager/Accountant | securely log in to my account using my email and password, with multi-factor authentication. | access my user profile and view food orders, historical data, and account details. | S1 | 4 | Multi-factor authentication must be supported. Role-based login permissions should be enforced. Password attempts should be limited to 5 retries before a lockout mechanism activates. | Connectivity Validation (CN): Ensure login works even with poor network, showing user-friendly error messages if a timeout occurs.
| 01.03 Manage User Profile | Diner/Restaurant Owner | edit/update my personal details, including my name, phone number, email, and address. | keep my information up to date and ensure my orders are correctly processed. | S1 | 4 | Users can only edit their own profile. Irrelevant user roles must have restrictions to prevent unauthorized changes to sensitive data. All updates must be logged for security audits. | Field Validation (FV): Ensure valid data formats for email, phone, address updates, and other relevant fields, with error prompts guiding users to correct mistakes.
| 01.04 Control Role-Based Access | System Administrator/Platform Manager | configure different permissions based on user roles. | ensure proper access control for different users, restricting or granting privileges as needed. | TBD | 4 | Only administrators can assign or change roles. All role changes should be logged, with timestamp and admin ID, for future audit purposes. Unauthorized users should be blocked from accessing role management options. | If role changes conflict with existing permissions or active sessions, unintended privilege escalation may occur.
| 01.05 View Order History | Diner, Restaurant Owner, Call Center Support, Technical Support Specialist | view a list of my previous orders, including dates, items, and total amounts. | track my past purchases and easily reorder my favorite meals. | S2 | 3 | Users should only see orders linked to their own accounts. Admins can access all orders but only via a secure dashboard with appropriate filters and logs. Unauthorized users must be restricted from viewing others. | If order data retrieval fails due to cache errors or incorrect query handling, users may not be able to view their order history.
02. Restaurant Management | 02.01 List Restaurants | Restaurant Owner, Technical Support Specialist | view a list of all available restaurants with their names, ratings, and cuisines. | choose a restaurant to order from or visit, based on my preferences. | S1 | 1 | Ensure restaurant listings respect user location filters. Large lists should be paginated or lazy-loaded to prevent performance issues. Sponsored restaurants must be clearly marked. | If the list fails to load due to slow internet connections, users may not see restaurant listings.
| 02.02 Search Restaurants | Restaurant Owner, Diners | search for restaurants based on keywords, location, or cuisine. | quickly find restaurants that match my taste or are nearby. | S1 | 1 | Enforce keyword matching rules and ranking algorithms, considering proximity, ratings, and sponsorship tiers. Invalid searches should return helpful suggestions instead of empty results. | If invalid characters or empty searches are entered, the system should return appropriate messages and prevent SQL injection or code injection vulnerabilities.
| 02.03 Browse Menu Items | System Admin, Restaurant Owner, Diners | view and explore the menu offerings of a selected restaurant, including item descriptions and prices. | decide what to order based on what’s available and within my budget. | S1 | 1 | Menus must display real-time data, reflecting item availability. Special offers or combos should be highlighted. Menu updates should sync instantly to avoid customer confusion. | If menu items are removed mid-session, users should be prompted to refresh or adjust their order, with clear error messages.
| 02.04 Manage Restaurant Profile | Restaurant Owner, Platform Manager | update my restaurant's profile information such as business hours, contact details, and address. | keep my restaurant details accurate and up to date for customers. | S1 | 1 | Restaurant owners can only edit their own profiles. Changes to business hours, address, and contact info must be validated for correctness and logged for review. | If invalid data formats are entered (e.g., incorrect phone number or address), the system should prompt the user to correct the errors.
| 02.05 Update Menu Offerings | Restaurant Owner | update my restaurant's menu items, including descriptions, prices, and availability. | keep my menu up to date and reflect current offerings. | S2 | 2 | Menu updates must be validated for correct pricing and availability. Changes should be logged for audit purposes. | If menu updates fail due to system errors, the system should notify the owner and prevent incorrect menu displays.
| 02.06 Manage Table Reservations | Restaurant Owner | manage table reservations for my restaurant. | optimize seating and ensure a smooth dining experience for customers. | S3 | 4 | Reservations must be validated for availability and logged for audit purposes. Overbooking should be prevented. | If reservation data is incorrect or unavailable, the system should notify the owner and prevent overbooking.
03. Order and Payment Processing | 03.01 Place Food Order | Diners | place an order for food items from a selected restaurant. | receive my desired meal at the specified location or for delivery. | S2 | 4 | Orders must include valid payment details and delivery address. Real-time updates on order status should be provided to the user. | If payment fails or the restaurant is unavailable, the order will not be processed, and the user will be notified.
| 03.02 Process Secure Payment | Platform Manager, Restaurant Owner, Technical Support Specialist | securely pay for my order using a trusted payment gateway. | complete my transaction without risking my financial information. | S3 | 4 | Payment transactions must be encrypted and comply with PCI-DSS standards. Only verified payment methods should be accepted. | If the payment gateway is unavailable or the payment method is invalid, the transaction will fail, and the user will be prompted to try again.
| 03.03 Track Commission Revenue | Platform Manager, Marketing Manager, Operations Manager | view the commission earned from each order. | monitor my earnings and ensure accurate revenue tracking. | TBD | 4 | Commission calculations must be accurate and based on predefined rates. Only authorized users (admins and restaurant owners) can access this feature. | If commission data is incorrect or unavailable, the system should log the error and notify the admin.
| 03.04 Manage Refunds and Cancellations | Platform Manager, Restaurant Owner, Call Center Support | request a refund or cancel an order. | resolve issues with my order and receive a refund if necessary. | S3 | 4 | Refunds must comply with the platform’s refund policy. Cancellations should be allowed only before the order is prepared. | If the order is already being prepared, the user will not be able to cancel it, and refunds will be processed according to the policy.
| 03.05 Generate Financial Reports | Operations Manager, Accountant, Restaurant Owner | generate detailed financial reports for my restaurant or the platform. | analyze revenue, expenses, and profitability. | S3 | 4 | Reports must include accurate data and be generated in a downloadable format (e.g., PDF, Excel). Only authorized users can access this feature. | If financial data is incomplete or incorrect, the system should notify the admin and prevent the generation of inaccurate reports.
04. Advertisement Management | 04.01 Create Ad Campaigns | Marketing Manager, Restaurant Owner | create and launch ad campaigns for my restaurant or platform. | attract more customers and increase visibility for my business. | S2 | 3 | Ad campaigns must include valid targeting options (e.g., location, cuisine, demographics). Budget limits must be enforced to prevent overspending. | If ad campaign creation fails due to invalid targeting or budget constraints, the system should notify the user and provide corrective suggestions.
| 04.02 Manage Sponsored Listings | Marketing Manager, Restaurant Owner | manage sponsored listings for my restaurant. | ensure my restaurant appears prominently in search results and listings. | S2 | 3 | Sponsored listings must comply with platform guidelines and budget limits. Only authorized users can manage sponsored listings. | If sponsored listings exceed the budget or violate guidelines, the system should block the action and notify the user.
| 04.03 Track Ad Performance | Marketing Manager, Restaurant Owner | track the performance of my ad campaigns and sponsored listings. | measure the effectiveness of my advertising efforts and optimize future campaigns. | TBD | 3 | Performance metrics (e.g., clicks, impressions, conversions) must be accurate and displayed in real-time. Only authorized users can access performance data. | If performance data is incomplete or unavailable, the system should notify the user and provide an estimated time for resolution.
| 04.04 Update and Optimize Content | Marketing Manager, Restaurant Owner | update and optimize the content of my ad campaigns and sponsored listings. | improve the effectiveness of my ads and attract more customers. | S3 | 3 | Content updates must comply with platform guidelines and ad policies. Only authorized users can update ad content. | If ad content violates guidelines or fails to update, the system should block the action and notify the user.
05. Finance & Operations | 05.01 Manage Financial Account | Operations Manager | manage my financial account, including bank details and payout preferences. | receive payments and manage my finances efficiently. | TBD | 4 | Financial accounts must be verified before payouts are processed. Only authorized users can access this feature. | If bank details are incorrect or incomplete, payouts will be delayed until the issue is resolved.
| 05.02 Generate Sales Reports | Accountant, Operations Manager | generate sales reports for my restaurant or the platform. | analyze sales performance and make data-driven decisions. | S3 | 4 | Reports must include accurate data and be generated in a downloadable format (e.g., PDF, Excel). Only authorized users can access this feature. | If sales data is incomplete or incorrect, the system should notify the admin and prevent the generation of inaccurate reports.
| 05.03 Process Payments | Operations Manager | process payments for orders and commissions. | ensure timely and accurate financial transactions. | S3 | 4 | Payments must be processed securely and comply with financial regulations. Only authorized users can access this feature. | If payment processing fails due to technical issues, the system should log the error and notify the admin.
| 05.04 Ensure Compliance with Financial Regulations | Operations Manager, Accountant | ensure that all financial transactions comply with legal and regulatory requirements. | avoid legal issues and maintain the platform’s credibility. | TBD | 3 | Financial transactions must be auditable and comply with local and international regulations. | If compliance checks fail, the system should block the transaction and notify the admin.
06. Platform Administration | 06.01 Manage User Accounts | Platform Manager | manage user accounts, including creating, updating, and deleting accounts. | ensure proper user management and access control. | TBD | 4 | Only administrators can manage user accounts. All changes must be logged for audit purposes. | If unauthorized users attempt to manage accounts, the system should block the action and notify the admin.
| 06.02 Monitor System Performance | System Admin | monitor the platform’s performance and uptime. | ensure the platform runs smoothly and efficiently. | TBD | 3 | Performance metrics must be tracked in real-time, and alerts should be sent for any anomalies. | If performance issues are detected, the system should notify the admin and provide troubleshooting recommendations.
| 06.03 Resolve Technical Issues | System Admin, Technical Support Specialist | resolve technical issues reported by users or detected by the system. | ensure a seamless user experience. | TBD | 4 | Technical issues must be logged and prioritized based on severity. Only authorized users can access this feature. | If technical issues cannot be resolved immediately, the system should notify the user and provide an estimated resolution time.
| 06.04 Deploy System Updates | System Admin | deploy system updates and patches. | keep the platform secure and up to date. | TBD | 3 | Updates must be tested in a staging environment before deployment. Only authorized users can access this feature. | If updates cause system instability, the system should roll back to the previous version and notify the admin.
| 06.05 Ensure Compliance | System Admin, Platform Manager | enforce platform-wide compliance policies, including regulatory, security, and operational standards. | ensure the platform operates within legal, security, and business regulations, minimizing risks and ensuring a smooth user experience. | TBD | 2 | Only System Administrators and Platform Managers should have access to configure compliance settings, review audit logs, and manage regulatory adherence. | Field Validations: Compliance rules must have valid date ranges, standardized formats, and cannot be left blank. Data Dependent Validations: Compliance settings must be aligned with regional laws (e.g., GDPR for EU users, CCPA for US users). Connectivity Validations: The system must validate real-time connections to external compliance monitoring tools or government databases when necessary. Data Driven Defaults: Default compliance settings should be pre-configured based on industry standards (e.g., automatic data retention policies)
| 06.06 Manage Digital Advertisements | Platform Manager | create, update, activate, deactivate, and remove digital advertisements on the platform. | ensure effective promotion of restaurants and offers while maintaining advertisement quality and compliance. | TBD | 2 | Only users with Platform Manager role should have access to manage digital advertisements. The role should have the necessary permissions to create, edit, publish, deactivate, and delete advertisements. Advertisements should comply with platform policies before being published. Certain actions (like publishing or deactivating) may require approval workflows depending on organizational settings. | Field Validations: Advertisement title should not exceed 100 characters. Description must be at least 50 characters long. Image file formats must be JPEG, PNG, or GIF, and the size should not exceed 5MB. Start and End dates should be in valid date format and cannot be in the past. Data Dependent Validations: Advertisements must be linked to at least one restaurant or category. Only restaurants registered on the platform can be advertised. An advertisement cannot have an overlapping time slot with an already active ad for the same restaurant. Connectivity Validations: The system should not allow ad creation if the internet connection is lost. If a draft ad is being edited and connectivity is lost, the system should auto-save progress. Data Driven Defaults: Default advertisement duration is 7 days unless specified otherwise. Default status of a newly created ad is "Draft" until published.
| 06.07 Analyze Ad Performance | Platform Manager | analyze the performance of advertisements running on the Bite Buddy platform by reviewing key metrics such as impressions, clicks, conversions, and ROI. | optimize ad strategies, allocate budgets effectively, and improve overall campaign performance to maximize revenue and user engagement. | TBD | 3 | Only authorized user roles should have access to ad performance data and insights. Access should be restricted based on permissions defined in the platform's role-based access control (RBAC) system. | Field Validations: Ensure that date ranges, numeric values, and filters applied to performance reports are valid and within acceptable limits. Data Dependent Validations: Ensure reports only fetch data from active ad campaigns and exclude expired or deleted campaigns. Connectivity Validations: If external analytics tools (such as Google Analytics or third-party ad platforms) are integrated, validate API connectivity before fetching data. Data Driven Defaults: Default report parameters should include the last 30 days of data, with filters for campaign type, region, and audience automatically applied based on user preferences.
07. Customer Support | 07.01 Track Order Status | Call Center Support, Technical Support Specialist | track the status of my order in real-time. | know when my order will be delivered. | S2 | 4 | Order status updates must be accurate and provided in real-time. Only authorized users can access this feature. | If order status updates are delayed or incorrect, the system should notify the user and provide an estimated delivery time.
| 07.02 Provide Chat Support | Call Center Support, Technical Support Specialist | provide real-time chat support to users. | resolve user queries and issues promptly. | TBD | 3 | Chat support must be available 24/7, and responses should be provided within a reasonable time frame. | If chat support is unavailable, the system should provide alternative support options (e.g., email, phone).
| 07.03 Submit Feedback | Restaurant Owners / Diners | submit feedback about my experience on the platform. | help improve the platform’s services. | S2 | 3 | Feedback must be categorized and prioritized based on user ratings and comments. | If feedback is submitted with invalid or inappropriate content, the system should flag it for review.
| 07.04 Rate Restaurant Experience | Restaurant Owners / Diners | rate my experience with a restaurant. | share my feedback and help other users make informed decisions. | TBD | 3 | Ratings must be based on a predefined scale (e.g., 1-5 stars) and include optional comments. | If ratings are submitted with invalid or inappropriate content, the system should flag them for review.
| 07.05 Manage FAQs | Call Center Support, Technical Support Specialist | manage frequently asked questions (FAQs) on the platform. | provide users with quick answers to common questions. | S2 | 2 | FAQs must be categorized and searchable. Only authorized users can manage FAQs. | If FAQs are outdated or incorrect, the system should notify the admin and prompt updates.
| 07.06 Manage Support Tickets | Call Center Support, Technical Support Specialist | manage support tickets submitted by users. | resolve user issues efficiently. | TBD | 4 | Support tickets must be prioritized based on severity and resolved within a predefined time frame. | If support tickets are not resolved within the expected time, the system should escalate them to higher-level support.